A3I

AI-Allowed Assessment Readiness Index

Prepared for Javier Jimenez
Research lead: Sam Abramovich, University at Buffalo
Working draft | August 2026

## Packet Contents

1. Project Overview: what A3I is, why it matters, and what we hope to build

2. Project Vocabulary and Concepts: education, assessment, data, and AI terms used in the project

3. First Assignment: Texas STAAR Data Reconnaissance

4. 100-Hour Fall Work Plan: phases, approximate hours, and deliverables

5. How We Will Work Together: research workflow, communication, and expectations

6. Technical Architecture and Data Flow: how raw public assessment materials become research data

HANDOUT 1

# Project Overview

Read this first. The goal is to understand the research problem before thinking about code.

## The Core Question

How many state-approved K-12 assessments can already be completed effectively by generative AI?

Generative AI can now produce essays, explanations, solutions, summaries, arguments, and other products that schools have historically treated as evidence of student learning. That creates an assessment-validity problem. If a student can generate a successful response with AI, the resulting product may no longer tell us what the student independently knows or can do.

Important distinction: This project is not a cheating-detection project. It asks whether the design of current assessments remains meaningful when powerful generative AI is widely available.

## Why State Tests Matter

K-12 education in the United States is highly decentralized. States establish academic standards and accountability systems, but daily curriculum and instruction are implemented by districts, schools, and teachers. State standardized assessments therefore function as a major policy lever: they signal which knowledge, skills, task formats, and performance criteria count as successful learning.

This produces the washback effect: teachers and schools adapt instruction to the demands of high-stakes assessments. If state tests emphasize source-based essays, classrooms tend to devote more time to source-based essays. If tests emphasize multi-step mathematical reasoning, instruction tends to devote more attention to that form of reasoning. The assessment system therefore affects more than testing days; it influences what students repeatedly practice throughout the school year.

STATE ASSESSMENT  →  CURRICULUM & ASSIGNMENTS  →  STUDENT PRACTICE  →  LEARNING

That is why AI susceptibility matters. If high-stakes assessments reward tasks that generative AI can complete easily, the washback effect may continue pushing classroom instruction toward products whose relationship to student learning has changed. A3I is intended to provide empirical evidence about the size and structure of that problem.

## What the Project Will Build

A structured public assessment corpus. Released test items, prompts, answer choices, scoring guides, rubrics, standards alignment, point values, and related metadata organized into a common schema.

An empirical AI benchmark. Once the source data are stable, selected generative AI systems can be run against released items to estimate which assessments they can complete and under what conditions.

An explanatory taxonomy. Item characteristics such as format, scoring mode, process requirements, source use, and point weighting can help explain why some items are more susceptible than others.

The A3I measurement framework. A transparent way to compare AI susceptibility across states, grades, subjects, assessment types, and eventually time.

Public-facing outputs. An open dataset, reproducible code, interactive dashboard, technical documentation, research papers, and policy briefs.

## Initial Geographic Scope

The larger research plan currently includes California, Texas, Massachusetts, New York, Virginia, Florida, Washington, and Ontario. The fall technical pilot will begin with Texas because the Texas Education Agency publishes substantial released STAAR material and supporting metadata.

## What Is Fixed vs. Still Being Designed

| Relatively fixed | Still provisional / research questions |
| --- | --- |
| Core problem: Determine what current standardized assessments generative AI can complete effectively. | A3I formula: Exact index construction and weighting are not finalized. |
| Source principle: Use authoritative public assessment materials and preserve provenance. | Benchmark protocol: Which models, prompts, repetitions, and scoring methods should constitute the benchmark. |
| Fall priority: Build a trustworthy Texas data foundation before scaling. | Taxonomy weights: Whether PPI/HJI/FRI or other constructs should be weighted, combined, or used only as explanatory variables. |
| Transparency: Methods, transformations, and assumptions should be reproducible and documented. | Scaling strategy: Which jurisdiction comes after Texas and how much automation can generalize. |

HANDOUT 2

# Project Vocabulary and Concepts

A working glossary. You are not expected to memorize this; use it as a reference.

| Term | Working definition |
| --- | --- |
| Assessment validity | The degree to which evidence and theory support the interpretations and uses of assessment scores. In A3I, a key question is whether an item still provides credible evidence of student learning when AI can produce the response. |
| Standardized assessment | An assessment administered and scored according to common rules so results can be compared across students, schools, or jurisdictions. |
| High-stakes assessment | A test whose results affect consequential decisions, such as accountability ratings, graduation, placement, or policy decisions. |
| Washback effect | The influence an assessment exerts on teaching and learning. Teachers often align curriculum, assignments, and practice with what high-stakes tests require. |
| Assessment blueprint | An official specification describing the content, standards, item types, reporting categories, and/or weighting of an assessment. |
| Released item | A test question that an assessment agency makes publicly available after administration or for practice. |
| Test form | A set of assessment items administered together. In Texas, released test forms reflect the STAAR blueprint for that administration. |
| Item | The smallest scorable assessment unit. One item may depend on a shared passage, table, graph, stimulus, or scenario. |
| Stimulus | Material needed to answer one or more items, such as a reading passage, chart, image, map, experiment description, or source set. |
| Selected response / MCQ | An item in which the student selects among provided answers. |
| Technology-enhanced item (TEI) | An item that uses interactive features such as drag-and-drop, graphing, multi-select, hot spots, equation entry, or other digital interactions. |
| Short constructed response (SCR) | An open-ended item requiring a relatively brief student-generated response. |
| Extended constructed response (ECR) | A longer open-ended response, often an essay or multi-paragraph written product. |
| Performance task | A multi-step or extended task intended to elicit application, reasoning, synthesis, or production rather than a single selected answer. |
| Scoring guide / rubric | Rules or criteria used to assign scores to student responses. |
| Exemplar / sample response | A sample student answer illustrating a particular score level or performance quality. |
| Point value | The number of raw score points associated with an item or task. Point values may later be used to weight the importance of different items. |
| Scoring mode | How an item is scored: machine, human, or hybrid. Hybrid systems combine automated scoring with human review or monitoring. |
| Process evidence | Evidence of how a student arrived at an answer, such as planning, intermediate work, justification, critique, revision, or use of sources. |
| Process signal | A coded feature indicating that an item explicitly requests some form of process evidence. |
| Provenance | Information about how an artifact was created, including tools, sources, transformations, or AI use. |
| AI susceptibility | The extent to which a generative AI system can produce a response that satisfies an assessment item and its scoring requirements. |
| AI robustness / resilience | The extent to which an item still elicits meaningful evidence of student learning even when generative AI is available. |
| Benchmark | A defined set of tasks and evaluation procedures used to compare AI system performance. |
| Corpus | A collected body of source material used for analysis. Here, the corpus consists of released assessment artifacts and metadata. |
| Schema | A formal specification for how data are represented, including field names, data types, relationships, and required/optional values. |
| Metadata | Data describing other data, such as jurisdiction, year, grade, subject, standard, item identifier, point value, and source URL. |
| Provenance record | A record that preserves where a source file or extracted item came from and how it was transformed. |
| Canonical representation | The standardized internal format used to represent heterogeneous source materials consistently across jurisdictions. |
| Human-in-the-loop | A workflow in which automated methods perform part of the work while humans review uncertain, ambiguous, or high-impact outputs. |
| Gold-standard sample | A subset of items carefully coded by humans and used to evaluate consistency, train automated methods, or validate later classifications. |
| Inter-rater reliability | The degree to which independent human coders assign the same codes to the same material. |
| A3I | AI-Allowed Assessment Readiness Index. Working name for the project’s measurement framework comparing how assessment systems fare in a generative-AI environment. |
| PPI | Process & Provenance Index. A provisional construct intended to represent how much an assessment elicits process evidence or provenance rather than only final products. |
| HJI | Human Judgment Index. A provisional construct representing the extent to which scoring requires human or hybrid evaluative judgment. |
| FRI | Format Robustness Index. A provisional construct representing how assessment formats differ in their susceptibility to AI completion. The definition and weighting are not final. |

HANDOUT 3

# First Assignment: Texas STAAR Data Reconnaissance

Estimated effort: approximately 10-12 hours. This is research reconnaissance, not a scraping assignment yet.

## Purpose

Before writing a data pipeline, we need to understand the Texas assessment information ecosystem. Your first task is to identify what authoritative STAAR materials exist, where they live, how they are organized, what metadata accompany them, and which formats will make automated acquisition difficult or easy.

Primary deliverable: A structured inventory of official Texas STAAR Reading Language Arts (RLA) and Mathematics/Algebra I resources that could contribute data to A3I.

## Authoritative Starting Points

Texas Education Agency: STAAR Released Test Questions — official TEA page

Texas Education Agency: STAAR overview/resources — official TEA STAAR resources

Texas Education Agency: STAAR Reading Language Arts Resources — official RLA resources

TEA currently publishes released online test forms plus supporting answer keys, item rationales, and student expectations tested. Because STAAR is now primarily online and includes technology-enhanced items, recent released tests may not be available as simple PDFs. That technical fact is itself important to document.

## Scope for the First Pass

Focus on RLA grades 3-8 plus English I and English II.

Focus on Mathematics grades 3-8 plus Algebra I.

Prioritize the most recent released administrations (start with 2026 and work backward through 2023).

Note older archives if they exist, but do not exhaustively catalog every historical file yet.

Use only official TEA or official Texas assessment platform sources for the authoritative inventory. Third-party practice sites do not count.

## For Each Resource, Record

| • Source URL | • Official resource title |
| --- | --- |
| • Year or administration | • Agency/platform |
| • Subject | • Grade/course |
| • File/interface type | • Resource type |
| • Answer key available? | • Item text accessible? |
| • Standards/expectations available? | • Item rationale available? |
| • Rubric/scoring guide available? | • Point/scoring information available? |
| • Shared stimulus dependency? | • Sample/exemplar responses available? |
| • Notes / unresolved questions • What else????? | • Technical barriers? |

## What Not to Do Yet

Do not attempt to scrape the entire Texas site.

Do not manually copy thousands of questions into a spreadsheet.

Do not run assessment items through an AI model yet.

Do not decide which items are "good" or "bad" assessments.

Do not invent missing metadata.

Do not use third-party test-preparation sites to fill gaps in official sources.

Do not transform or rename source content without preserving the original source URL and original file/title information.

## Definition of Done

1.  We can answer what official RLA and mathematics resources Texas makes available for the target years/grades.

2.  We understand which information is available at the item level and which exists only at the test-form or blueprint level.

3.  We have documented the major file/interface types we will need to ingest.

4.  We can identify a tractable first subset for automated acquisition and extraction.

5.  Another researcher could use your inventory to find the same source materials without retracing your entire search process.

## Files to Return

A structured inventory in CSV or spreadsheet form.

A short README explaining scope, naming conventions, and anything another researcher needs to understand the inventory.

A ~200 word reconnaissance reflection addressing: What surprised you about the Texas data? What looks straightforward to automate? What looks technically difficult? What decisions do we need to make before building the ingestion pipeline?

HANDOUT 4

# 100-Hour Fall Work Plan

This is a planning framework, not a rigid timesheet. Research discoveries may shift hours among phases.

| Phase | Hours | Primary Focus | Main Deliverable |
| --- | --- | --- | --- |
| 1. Orientation | 8 | A3I, assessment basics, Git/GitHub, project conventions. | Working environment + project understanding. |
| 2. Data reconnaissance | 12 | Map Texas STAAR RLA/math sources and metadata. | Source inventory + reconnaissance reflection. |
| 3. Acquisition pipeline | 20 | Reproducible downloading and source registration. | Scripts + source manifest + raw archive conventions. |
| 4. Extraction & schema | 30 | Extract item/stimulus/answer/rubric metadata. | Structured Texas dataset + schema documentation. |
| 5. QA & validation | 15 | Errors, duplicates, missing fields, provenance, edge cases. | QA report + corrected pipeline/dataset. |
| 6. AI benchmark prototype | 10 | If ready, controlled model-evaluation proof of concept. | Pilot results on a limited clean sample. |
| 7. Documentation & handoff | 5 | Make work reproducible for another researcher/developer. | README, setup notes, issues, next steps. |

TOTAL PLANNED HOURS: 100

## Suggested Weekly Rhythm

Approximately 6-7 project hours per week on average, adjusted around coursework.

One fixed 30-minute research meeting each week during active development.

Independent work organized around one or two clearly defined issues/tasks at a time.

HANDOUT 5

# How We Will Work Together

Research software is iterative. The goal is to make uncertainty visible, decisions traceable, and work reproducible.

## What I Expect From You

Be curious and precise. Ask why a source, field, or transformation exists rather than treating the task as data entry.

Surface uncertainty. If a requirement is ambiguous, flag it instead of silently making a consequential research decision.

Preserve provenance. We should always be able to trace an extracted item back to its official source.

Commit small, understandable changes. Frequent commits are easier to review, debug, and learn from than large unexplained changes.

Document failures. A failed approach can be useful research knowledge if we know what was tried and why it failed.

Prefer reproducibility over one-time success. A script that works reliably is more valuable than a manual workaround that cannot be repeated.

Protect the research question. Do not simplify the data just because a technically difficult feature is inconvenient. Flag the problem and we will decide together whether the feature matters scientifically.

## What You Should Expect From Me

Clear, bounded assignments rather than an expectation that you solve the entire project.

Context about why the work matters, not just instructions about what to code.

Weekly access for questions, decisions, and review – or more frequent depending on need.

Feedback on both technical work and research reasoning.

Increasing autonomy as you become familiar with the data and project.

Credit appropriate to your contribution on research products that grow from this work.

## The "Stuck" Rule

If you are stuck for roughly 30-60 minutes and do not know what useful experiment to try next: Stop digging. Write down (1) what you were trying to accomplish, (2) what you tried, (3) what happened, (4) any error messages or evidence, and (5) your best guess about the problem. Then email it to me. Being stuck is normal; being silently stuck for five hours is avoidable.

## Weekly Status Format

| Completed | What is working or finished since the previous meeting? |
| --- | --- |
| Attempted / learned | What did you test or discover, including approaches that failed? |
| Blocked / decisions needed | What requires input, clarification, access, or a research decision? |
| Next | What is the next bounded task you expect to complete? |

## Research Conduct for Public Data

Use official public sources unless explicitly asked to investigate secondary sources.

Do not bypass access controls, authentication, robots restrictions, or other technical protections without discussing it first.

Keep raw source files separate from transformed/derived data.

Do not overwrite source artifacts. Transformations should create new derived files/records.

Record source URL, retrieval date, and relevant identifiers whenever feasible.

If a source changes or disappears, document the issue rather than silently replacing it with something else.

HANDOUT 6

# Technical Architecture and Data Flow

This is the current conceptual architecture. Components may change as the Texas pilot reveals what the data actually require.

## End-to-End Flow

1. Official source ecosystem TEA pages, released online test forms, PDFs, scoring guides, rubrics, answer keys, blueprints, standards metadata.

↓

2. Source registry A manifest describing every source artifact: URL, title, year, subject, grade/course, resource type, retrieval date, format, and status.

↓

3. Acquisition layer Scripts or controlled procedures that retrieve/archive accessible source materials reproducibly.

↓

4. Raw archive Immutable copies or references to source artifacts. Raw data should not be "cleaned" in place.

↓

5. Extraction layer Parse documents/interfaces into item text, answer choices, stimuli, correct answers, rationales, standards, rubrics, point values, and other fields.

↓

6. Canonical item schema Represent heterogeneous Texas items in a consistent machine-readable format while retaining source-specific information.

↓

7. QA / human validation Check completeness, item boundaries, stimulus relationships, answer mappings, duplicates, and provenance.

↓

8. Analytical coding Apply explanatory metadata such as format, scoring mode, process signals, and provisional A3I taxonomy codes.

↓

9. AI benchmark Present clean items to defined models under controlled protocols and score outputs against official answers/rubrics.

↓

10. Analysis & public outputs Estimate AI susceptibility, compare item types/subjects/jurisdictions, and support dashboard, papers, policy briefs, and open data releases.

## Candidate Canonical Item Fields???

jurisdiction, assessment_program, administration_year, grade_or_course, subject, test_form_id, item_id, item_number, item_type, prompt_text, stimulus_id(s), answer_choices, official_answer, item_rationale, standard_or_expectation, point_value, rubric_or_scoring_guide, scoring_mode, source_url, source_resource_id, retrieval_date, raw_artifact_path/reference, extraction_method, qa_status, notes

Never sacrifice traceability for convenience. A derived record should be traceable back to an official source and, where possible, to the specific source artifact and location from which it was extracted.

## What Success Looks Like at the End of the Fall

A new developer can clone/open the project and understand how the Texas pilot works.

We have a documented inventory and reproducible source-acquisition process.

We have a clean structured subset of Texas STAAR items with reliable provenance.

Known extraction failures and edge cases are explicitly documented.

We know what parts of the pipeline can generalize to another jurisdiction and what parts are Texas-specific.

If the data quality is sufficient, we have a small AI benchmark prototype and a much better basis for designing the full evaluation protocol.